Enhancing Education Through Technology’s (E2T2)

Grant Writing Schedule & Agendas 

 SY 09-10

****Meetings will be held at St. Mary’s Elementary School’s Media Center at 9:30.

****Staff from the following schools will attend the meetings to collaborate regarding technology needs & plans:  St. Mary’s Elementary School, St. John’s-St. Andrew’s School, Sacred Heart School, & Melrose ISD

September 2009


All Schools put together Tech Wish List

October 2, 2009


Construct District Technology Surveys







*Teachers







*Parents






Compile Surveys






Collect Data that would be helpful for grant

November 13, 2009


Needs Assessment:







*Review Survey Data







*Review Inventories







*Review Wish Lists  







*Include Research to support needs







*Include assessment data

December 4, 2009


Project Summary






Budget Summary






Budget Narrative

January 8, 2010


Narrative

*Statement of Need & Needs Assessment

February 5, 2010


Proof Narrative & Revise






If time allows, begin Assessment

March 12, 2010


Finish Assessment Sections

                                                   

*Project Scope & Development







*Goals & Objectives of the Project







*Work Plan







*Evaluation of Outcomes

April 9, 2010



Cover Sheet






Assurances

May 7, 2010



Review & Submit

